## Sheet1
Test Case ID | Scenario ID | Module | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC_LOGIN_001 | TS_LOGIN_001 | Login | 1. Open SauceDemo 2. Enter valid username 3. Enter valid password 4. Click Login | standard_user / secret_sauce | User should login and Products page should display | Pending | Not Executed | High
TC_LOGIN_002 | TS_LOGIN_002 | Login | 1. Open SauceDemo 2. Enter valid username 3. Enter invalid password 4. Click Login | standard_user / wrong123 | Error message should display and user should not login | Pending | Not Executed | High
TC_LOGIN_003 | TS_LOGIN_003 | Login | 1. Open SauceDemo 2. Enter invalid username 3. Enter valid password 4. Click Login | invalid_user / secret_sauce | Error message should display | Pending | Not Executed | High
TC_LOGIN_004 | TS_LOGIN_004 | Login | 1. Open SauceDemo 2. Keep username blank 3. Enter password 4. Click Login | blank / secret_sauce | Username required error should display | Pending | Not Executed | Medium
TC_LOGIN_005 | TS_LOGIN_005 | Login | 1. Open SauceDemo 2. Enter username 3. Keep password blank 4. Click Login | standard_user / blank | Password required error should display | Pending | Not Executed | Medium
TC_LOGIN_006 | TS_LOGIN_006 | Login | 1. Open SauceDemo 2. Enter locked user credentials 3. Click Login | locked_out_user / secret_sauce | Locked user error should display | Pending | Not Executed | High
TC_LOGIN_007 | TS_LOGIN_007 | Login | 1. Open SauceDemo 2. Type password in password field | secret_sauce | Password should be masked | Pending | Not Executed | Medium
TC_LOGIN_008 | TS_LOGIN_008 | Login | 1. Login with valid credentials 2. Observe landing page | standard_user / secret_sauce | User should land on Products page | Pending | Not Executed | High

## Sheet2
Test Case ID | Scenario ID | Module | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC_PRODUCT_001 | TS_PRODUCT_001 | Product Listing | 1. Login with valid credentials 2. Observe Products page | standard_user / secret_sauce | Product list should display | Pending | Not Executed | High
TC_PRODUCT_002 | TS_PRODUCT_002 | Product Listing | 1. Login 2. Check product names on product cards | N/A | Product names should be visible | Pending | Not Executed | Medium
TC_PRODUCT_003 | TS_PRODUCT_003 | Product Listing | 1. Login 2. Check product prices | N/A | Product prices should be visible and correctly formatted | Pending | Not Executed | Medium
TC_PRODUCT_004 | TS_PRODUCT_004 | Product Listing | 1. Login 2. Check product images | N/A | Product images should display properly | Pending | Not Executed | Medium
TC_PRODUCT_005 | TS_PRODUCT_005 | Product Listing | 1. Login 2. Select sorting option Price low to high | Sort: Low to High | Products should sort by price ascending | Pending | Not Executed | Medium
TC_PRODUCT_006 | TS_PRODUCT_006 | Product Listing | 1. Login 2. Select sorting option Price high to low | Sort: High to Low | Products should sort by price descending | Pending | Not Executed | Medium

## Sheet3
Test Case ID | Scenario ID | Module | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC_DETAILS_001 | TS_DETAILS_001 | Product Details | 1. Login 2. Click any product name | N/A | Product details page should open | Pending | Not Executed | High
TC_DETAILS_002 | TS_DETAILS_002 | Product Details | 1. Open product details page 2. Observe product name | N/A | Correct product name should display | Pending | Not Executed | Medium
TC_DETAILS_003 | TS_DETAILS_003 | Product Details | 1. Open product details page 2. Observe product description | N/A | Product description should display properly | Pending | Not Executed | Medium
TC_DETAILS_004 | TS_DETAILS_004 | Product Details | 1. Open product details page 2. Observe product price | N/A | Product price should display correctly | Pending | Not Executed | Medium
TC_DETAILS_005 | TS_DETAILS_005 | Product Details | 1. Open product details page 2. Click Back to Products button | N/A | User should navigate back to products page | Pending | Not Executed | Medium

## Sheet4
Test Case ID | Scenario ID | Module | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC_CART_001 | TS_CART_001 | Cart | 1. Login 2. Click Add to Cart on any product | Sauce Labs Backpack | Product should be added to cart | Pending | Not Executed | High
TC_CART_002 | TS_CART_002 | Cart | 1. Add product to cart 2. Observe cart badge count | 1 Product | Cart badge count should update correctly | Pending | Not Executed | High
TC_CART_003 | TS_CART_003 | Cart | 1. Add product 2. Open cart page | Sauce Labs Backpack | Added product should display in cart | Pending | Not Executed | High
TC_CART_004 | TS_CART_004 | Cart | 1. Add product 2. Open cart page 3. Verify product name | Sauce Labs Backpack | Correct product name should display | Pending | Not Executed | Medium
TC_CART_005 | TS_CART_005 | Cart | 1. Add product 2. Open cart page 3. Verify product price | Product Price | Correct product price should display | Pending | Not Executed | Medium
TC_CART_006 | TS_CART_006 | Cart | 1. Add product 2. Open cart page 3. Click Remove | Sauce Labs Backpack | Product should be removed from cart | Pending | Not Executed | High
TC_CART_007 | TS_CART_007 | Cart | 1. Remove all products from cart | N/A | Cart should become empty | Pending | Not Executed | Medium
TC_CART_008 | TS_CART_008 | Cart | 1. Open cart page 2. Click Continue Shopping | N/A | User should navigate back to products page | Pending | Not Executed | Medium